## Xanthe Sharp Activity Log
Name: |  | Project Group (Name/Number):
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Spoke with the group outside of the session to discuss our ideas. Ideas included a gardening app, horoscopes app, platform to arrange meeting at conferences. Made jam board of SWOT analysis for the team. | 1 | Yes | Aims for next Tues: Overall Find relevant APIs, add to jamboard/pinned post Tutorials on how to make similar functions were hoping to make (for example making a log book), add to jamboard in section Find similar apps that already exist, add to jamboard This could be because of their functionality, or how the front end looks etc. Specific Database: Think about database structure for logbook/in general What tables we could need (for e.g., one per user for their individual logbooks (?), one for summer growing plants etc) What fields are needed in each of the tables Jamboard link: https://jamboard.google.com/d/1xCdy50tL8VKSHgkb0oI6czvc-gPpRNgBO0lU6qD0iXU/edit?usp=sharing (edited)
1 | 2023-04-29 | Review APIS for possible apps. | 2 | yes
1 | 2023-04-30 | Created plant app flow diagram to help communicate ideas. Made edits /additions to inital report. | 1.5 | yes | A few of us made flow diagrams to compare and discuss
2 | 2023-05-01 | Meeting. Decided on plant app and started dividing out tasks. | 1 | Yes
2 | 2023-05-02 | Spoke with the group outside of the session to discuss our ideas. Discuss week 2 homework and combine aims and information for the app. | 1 | Yes
2 | 2023-05-03 | Meeting to discuss our ideas. Decide to make own plant api database as some have lots of missing info and then we have more control over the data. | 1 | Yes
2 | 2023-05-05 | Discussed ideas on slack. Bethan to be pm. | 1 | Yes
2 | 2023-05-06 | Created code to put json data into tables. Looked at possible MySQL or Pandas. Created Pandas solution and MySQL solution (would need debugging). However ultimately wasn't used for the project as the data was being stored online which I hadn't realised. | 3 | No
2 | 2023-05-07 | Meeting to review report (homework 2) submission and look at the base code. | 1 | Yes | Base code allows the user to do the following atm: Creates tables + plant DB Populates plant tables (ID and requirements) User log in Search for plants to add to their logbook View their logbook
3 | 2023-05-08 | Created code for the weather search section. Integrated the open weather map and ambee apis within functions to display the required infomration for the user. | 3 | Yes | Sarah has also worked on this, we'll combine our code
3 | 2023-05-14 | Added if statements to weather code to print messages according to temp and UV levels. Refactored the weather code to break it down into smaller functions, for easier testing. | 2 | yes
4 | 2023-05-15 | Started to work on the report, read and thought about the different sections, added some info to the introduction | 15 mins | no
4 | 2023-05-18 | Added content to the Background section of the report | 30 mins | no | Seek further clarification about what info needed for the Testing section
4 | 2023-05-20 | Wrote tests for the Weather page. Lots of functions to test and some took a bit of thinking about, therefore took me some time! | 4 | yes
4 | 2023-05-20 | Zoom meeting, discussed some issues still needing attention and discussed the project report. To meet again on Monday and split the remaining work. | 1 | Yes
4 | 2023-05-24 | Meeting, discussed loose ends to tie up. | 45 mins | Yes | I will focus on the report
4 | 2023-05-25 | Writing content for the report | 2 | No | Have added fair amount of content but others can add their expertise and further detail / diagrams.
4 | 2023-05-27 | Meeting to look at remaining work | 1 | Yes
4 | 2023-05-27 | Tried to complete unit tests for login section, but these functions were too complex for me so had to ask others for help here. Sarah and Aimee were able to complete them. | 20 mins | No
4 | 2023-05-27 | Editing report | 30 mins | Yes
Total time:

## Laura Cullen Activity Log
Name: Laura Cullen |  | Project Group (Name/Number): Group 2 Bloom x Labs
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Spoke with the group outside of the session to discuss our ideas. Ideas included a gardening app, horoscopes app, platfrom to arrange meeting at conferences. Made jam board of SWOT analysis for the team. | 1 | Yes
1 | 2023-04-29 | Review APIS for possible apps. | 2 | yes
1 | 2023-04-30 | Expand on report for homework 2. Create sample flowchart of app (plants) | 1.5 | yes
2 | 2023-05-01 | Decided on plant app and started dividing out tasks. | 1 | Yes
2 | 2023-05-02 | Spoke with the group outside of the session to discuss our ideas. Discuss week 2 homeowrk and combine aims and information for the app. | 1 | Yes
2 | 2023-05-03 | Spoke with the group outside of the session to discuss our ideas. Decide to make own plant api database as some have lots of missing info and then we have more control over the data. We divide this up between ourselves and I take vegetables. | 1 | Yes
2 | 2023-05-04 | Trello board created and task added | 0.2 | yes
2 | 2023-05-05 | Generate vegetables for api. | 1 | yes
2 | 2023-05-05 | Discussed ideas on slack. Bethan to be pm. | 1 | Yes
2 | 2023-05-07 | Spoke with the group outside of the session to review report (homework 2) submission and look at the base code (using SD's base code) | 1 | Yes
3 | 2023-05-08 | Review basic base code on own branch. Still needs to be merged to main. | 2 | Yes
3 | 2023-05-09 | Look at file and folder structure | 2 | Yes
3 | 2023-05-09 | Look at file and weather API and connection/ implementation within the app | 1 | Yes
3 | 2023-05-09 | Design logo and naming options | 1.5 | Yes
3 | 2023-05-09 | Spoke with the group outside of the session to divide code and tasks. Report completed and submitted. | 1 | Yes
3 | 2023-05-10 | Meeting with Bethan to resolve folder structure, divide functions and make classes. | 1 | Yes
3 | 2023-05-11 | Look at the run file, databases, homepage and login and create classes and break up the code into functions. Adding a few additional functions that will be needed. | 3 | Yes
3 | 2023-05-12 | Create pull request for review and merge with main branch | 0.5 | Yes
3 | 2023-05-12 | Group discussed when next to meet on Slack. Majority were available on Monday evening after class. | 0.25 | Yes
3 | 2023-05-12 | discussion thread for the weekend as some team members wanted to to meet earlier. Suggested someone else could be PM + asked if we wanted to get rid of Trello as we haven't been active on it. | 0.25 | Yes
4 | 2023-05-15 | Create search and logbook classes and tidy code. Create classes for database functions and run function. Coordinate imports. | 6 | Yes
4 | 2023-05-15 | Spoke with the group outside of the session to decide whats next and explain code formatting and file structure. LC Nominated to be PM this week. Name to be Bloom x labs. | 0.5 | Yes
4 | 2023-05-16 | Review and merge all outstanding pull requests. Tidy code and get main branch up to date. Work on database, login, homepage and api code. | 3 | Yes
4 | 2023-05-17 | Spoke with the group outside of the session | 0.5 | Yes
4 | 2023-05-18 | Review and merge all outstanding pull requests and branches. | 3 | Yes
4 | 2023-05-19 | Push changes | 1 | Yes
5 | 2023-05-22 | Try and get code running. Merge database files into one. Add helper function to within functions. Review Sarahs commetns and make changes. | 7 | Yes
5 | 2023-05-23 | Get run.py working for login and homepage then to connect to the exit and weather functions from otherfiles. Further amendments to the database file to enable creation of the datbase itself as well as tables. | 5 | Yes
5 | 2023-05-23 | Spoke with the group outside of the session to try and get the code working. | 0.5 | Yes
5 | 2023-05-24 | Review and merge all Sarahs working code!! | 0.5 | Yes
5 | 2023-05-23 | Spoke with the group outside of the session to divide remaining tasks. | 0.5 | Yes
5 | 2023-05-24 | Minor amendments and pushing of full working code. | 0.5 | Yes
5 | 2023-05-25 | Create app architecture diagram | 1 | Yes
5 | 2023-05-26 | Create gaant chart | 1 | Yes
5 | 2023-05-27 | Spoke with the group outside of the session to divide remaining tasks. | 0.5 | Yes
5 | 2023-05-27 | Write readme.py file | 0 | Yes
5 | 2023-05-27 | Write testing for homepage and database | 4 | Yes
5 | 2023-05-27 | Update and manage github | 2 | Yes
5 | 2023-05-28 | Checked final code. Minor changes to get it working and final commit | 1 | Yes
5 | 2023-05-28 | Final check through report (looks very good thankyou team!) and logbooks. | 0.5 | Yes
5 | 2023-05-28 | Commit logbooks, report and chosed logo to github. FINAL SUBMISSION WOO. | 0 | Yes
Total time:
61.2

## Sarah Dowd Activity Log
Name: |  | Project Group (Name/Number): Group 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Primary group meeting to discuss app ideas including a gardening app, horoscopes app, conference organisation app. Created a jam board of SWOT analysis for the team to contribute to and shared with group after meeting as an img. | 1 | Yes
1 | 2023-04-27 | Researched available API's for app ideas and learnt about API key's and requirements for inserting them in code | 1.5 | Yes | API Research: Github link to public-APIs (https://github.com/public-apis/public-apis) and GrowStuff: https://github.com/Growstuff/growstuff/wiki/API-Version-0
1 | 2023-04-27 | Looked at videos for how to use Trello and then created a google drive account to store work in | 0.5
2 | 2023-05-01 | Meeting to confirm that we are creating a plant app and splitting up tasks | 1 | Yes
2 | 2023-05-02 | Group meeting to discuss an initial flowchart for the app - discussing key app requirements and 'nice to have' functionalities. | 1 | Yes
2 | 2023-05-03 | Group meeting post API-Searching to discuss making own plant api database as lots of the APIs available online for plants were incomplete. | 1 | Yes
2 | 2023-05-03 | Wrote ChatGPT Prompts to request it to source publicly available plant information for us (common name, latin name, class, light conditions etc...) to insert into a .json file then contributed to the .json file. | 2 | Yes
2 | 2023-05-04 | Contacted instructors to confirm that we would be able to use our own .json files and shared feedback with the group. Also tried to review the previous messages group had sent regarding database functionality and asked if we could have a meeting saturday to discuss merging everyones ideas. | 0.5 | Yes
2 | 2023-05-05 | Drew a draft flowchart for the app functionality / backend and started a thread for other members of the group to add their flowchart ideas (to later merge) | 0.5 | Yes
2 | 2023-05-05 | Suggested we have a scrum/team leader on slack for each week and that we have a poll to arrange our next meeting due to it being a bank holiday weekend and got up to date with slack messages on main group thread such as reviewing other group members flowchart ideas. | 0.5 | Yes
2 | 2023-05-06 | Combined all plant dictionary creations completed so far by team members (in a word doc) into a .json file and uploaded publicly to use to create base code | 0.5 | Yes | The .json file will be improved later in the project by another team member to make sure all of the ChatGPT output makes sense / is not gibberish. Used .json formatter to check for any errors: https://jsonformatter.curiousconcept.com/
2 | 2023-05-06 | Wrote code (shared on slack) for taking the dictionary of plants from the .json file (hosted online in a public github) and insert into MySQL database. Also wrote the code to create the MySQL tables and use INSERT INTO to put the .json code into the new tables. | 2 | Yes | Had to learn how to make menu function and revise how to insert information from .json files into MySQL databases
2 | 2023-05-06 | Finished writing base code for basic app functionality for people to edit and adapt - shared via slack / github. Finished adding comments to it today to tell people how it works / what each bit does. | 4 | Yes | Base code allows the user to do the following: create tables and plant database, populate the plant tables, user login, search for plants to add to their logbook, view their logbook.
2 | 2023-05-07 | Group Meeting with Bethan, Xanthe - to show how the base code works and to discuss tasks moving forwards. Also worked on a new flowchart for the app together on a live google slide so we could ask another group member if they could help us present it in a more formatted way. | 1 | Yes
2 | 2023-05-07 | Came up with some plant app name ideas and branding (logo) and started a thread to get other group members ideas for creative company names etc. | 0.5 | Yes | BloomBuddy - made a logo idea
3 | 2023-05-08 | Created a google doc file to be shared - used by myself and Bethan to write down what the program (base code) has and what it doesn't do so far to meet app requirements so we can start to divide tasks in our next group meeting. Also to check that everyone had a chance to review the current code functionality. | 1 | Yes | Comments made on this by myself and Bethan.
3 | 2023-05-08 | Researched weather APIs to use for the weather section of the app and started writing some weather code. Also helped Xanthe via slack messages to trouble shoot some weather code for calling an API (that required a header to authenticate the requests) as she is also writing some weather code so we can compare and merge our codes later in the week. | 2 | Yes | Myself and Xanthe both found the same API to be the best for weather and started to write the code individually to later merge
3 | 2023-05-09 | Finished off the written report to submit - edited the input from other group members to tidy up the 'What does it do or what kind of problem does it solve' section, also included statistics in this section about other plant apps (referenced), made it look nice with headers etc, finished the SWOT analysis section and made sure the references were harvard referenced. | 3 | Yes | Including researching the app market / target user market for the app.
3 | 2023-05-10 | Team coding meeting with Xanthe and Laura DP, edited Xanthes base code for the weather section to merge in my own code also to integrate another API for pollen count and also an API for checking user location based on their postcode (to return latitude and longitude) | 2 | Yes | http://api.postcodes.io and https://api.ambeedata.com/latest/pollen/
3 | 2023-05-12 | Group discussed when next to meet on Slack. Majority were available on Monday evening after class. Separate thread on slack also used to discuss not using Trello as team not using it so far to track tasks - using slack instead / regular stand-up meetings. | 0.5 | Yes
3 | 2023-05-13 | Continued to work on weather API code to re-write the print statement functions. | 1 | Yes | This was then able to be used by Xanthe to also separate the functions and rename the print one print_summary and customise the temp/UV levels.
3 | 2023-05-14 | Added if statements to weather code to print messages to offer User advice based on the Pollen count data. Re-wrote the print statements to allow the code to print clearly for the user and changed pollen count data so it created a list of different pollen types and specific advice for each type. | 2 | Yes | Kept running into problems with publishing the pollen statements on different lines.
| 2023-05-15 | Group meeting to decide what is next to do and for Laura Cullen to go through the file structure / nominate LC as scrum master for the next week. | 1 | Yes
4 | 2023-05-15 | Researched how to make flask apps to try and transform the current weather section into a flask app that runs. | 3 | Yes | Re-watched old sessions on making flask apps and revisited flask app work we had done with course instructors.
4 | 2023-05-16 | Learnt how to make a html index page to allow the flask app for the weather section to run. | 2 | Yes | App will not be used as front end not required (after discussions with instructors) but good practise to learn how to use the flask package in python and create html front ends.
4 | 2023-05-17 | Group meeting with the group to discuss new PM, aiming to get sections working in functions, and send messages to instructor to ask for advice regarding navigation. | 1 | Yes
4 | 2023-05-19 | Went through current code on GitHub to try and get it to run and see if i could spot any errors - some circular import errors with code etc, wrote all of them down to share with group at next meeting. | 3 | Yes | Was trying to wrap my head around the different bits of code / why we were running into 'circular import' errors - had to search what they were / how to fix them.
4 | 2023-05-20 | Group meeting with Bethan, Laura DP, Xanthe Sharp - went through some of the errors I had noticed so far and shared the txt document file of spotted errors / possible solutions for people to check. Also looked at the examples shared by Youri/Bethan for previous project documentation of another group to get an idea for what we need to do for the final project report. | 1.5 | Yes
4 | 2023-05-21 | Tried to review other group members code but not fully complete yet so struggled trying to run some of the code - will wait for GitHub to be updated. | 2 | No | Was trying to edit some of the current code on GitHub but not able to edit other peoples sections as not sure I have the updated / most recent copies - will wait and see if anyone needs help and offered help recently on slack in meeting for troubleshooting code if needed!
5 | 2023-05-23 | Updated project activity log for my own activity log | 1.5 | Yes
5 | 2023-05-23 | Spent time trying to get the project to work - updating the logbook.py and database.py files as well as changing the homepage/run file to 'talk' to the different parts of the program | 4 | Yes | Including sorting code from Laura DP into classes and re-writing quotes python file to import a URL rather than a local file.
5 | 2023-05-25 | Researching gantt charts for project report | 0.25 | Yes | Not required - created by Laura Cullen
5 | 2023-05-27 | Changed some of the logbook.py code to do handling of exceptions and created a testing file for the logbook.py file.. | 3 | Yes | Still needs more tests from other team members also
5 | 2023-05-27 | Attended group meeting on slack and replied to slack comments - final day of working on project | 2 | Yes

## Aimée Szkolar Activity Log
Name: Aimée Szkolar |  | Project Group (Name/Number): Group 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Inital group meeting to discuss ideas. Plant app, horoscope app and conference app suggested. Jam board of SWOT analysis created | 1 | Y
1 | 2023-04-27 | Group meeting, Plant app decided on. Research into API's and current software currently on the market done | 1.5 | Y
2 | 2023-05-02 | Discussed the use of Trello, reseach done on how to use Trello | 0.5 | Y
2 | 2023-05-02 | Discussion on HW2 with group outside of session | 1 | Y
2 | 2023-05-03 | Generation of .json file discussed to give us more control of the data. Agree to deligate out fairly. I took fruit. | 1 | Y
2 | 2023-05-05 | Generated fruits data for .json file | 1 | Y
2 | 2023-05-07 | Meeting to discuss progress and work on base code. Tasks allocated out and given try/except functions | 1.5 | Y
3 | 2023-05-09 | Meeting with Laura C and Bethan. Work on file structure and continuation of function separation | 1 | Y
3 | 2023-05-10 | Meeting. Assigned logbook code to work on | 1 | N | Code reviewed and some intial work started. Not yet finished
3 | 2023-05-11 | Discussion about documentation for the final project | 0.5 | Y
3 | 2023-05-14 | Work on breaking up logbook into classes and smaller functions | 2 | N | Further work needed for code to run
4 | 2023-05-15 | Meeting. Deadlines set for code to be finished. Discussion how different files work together | 1 | Y
4 | 2023-05-16 | Ideas for logo discussed. Added a suggested logo to the thread with the agreed name | 0.5 | Y
4 | 2023-05-20 | Further work on logbook code | 2 | N | Still some errors
5 | 2023-05-22 | Logbook code posted in group and shared for review | 1 | Y | Code runs but needs commenting
5 | 2023-05-23 | Run fuction added to logbook code | 1 | Y
5 | 2023-05-24 | Meeting with group. Discussed next steps and to ask for review from lecturer | 1 | Y
5 | 2023-05-27 | Work on testing for logbook | 1 | N | Could not get the section of code to work, asked for help from team
5 | 2023-05-27 | Work on testing for login | 1 | N
5 | 2023-05-27 | Adding to report | 0.3 | Y

## Bethan Hoare Activity Log
Name: Bethan Hoare |  | Project Group (Name/Number): Group 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Group meeting during intro to project class to discuss our ideas. App ideas included a gardening app, horoscopes app, platform to arrange meeting at conferences. Group made jamboard of SWOT analysis, each member contributed their own. | 1 | Yes
1 | 2023-04-27 | Group meeting outside of class to choose an idea to narrow down API research. Added zoom link to Slack to use after class. Group chose gardening app, and discussed what aims we had over the weekend. Decided on finding relevant APIs, looking for similar exisiting apps, finding tutorials/stackoverflow for some functions e'd like to create in the app and how we are going to structure our database. Aim to add research to jamboard. | 1 | Yes
1 | 2023-04-27 | Made post on slack detailing tasks | 0.25 | Yes | Aims for next Tues: Overall Find relevant APIs, add to jamboard/pinned post Tutorials on how to make similar functions were hoping to make (for example making a log book), add to jamboard in section Find similar apps that already exist, add to jamboard This could be because of their functionality, or how the front end looks etc. Specific Database: Think about database structure for logbook/in general What tables we could need (for e.g., one per user for their individual logbooks (?), one for summer growing plants etc) What fields are needed in each of the tables Jamboard link: https://jamboard.google.com/d/1xCdy50tL8VKSHgkb0oI6czvc-gPpRNgBO0lU6qD0iXU/edit?usp=sharing (edited)
1 | 2023-04-28 | Researching APIS that we could use to search for gardening info, found a few about farming + indoor gardnening. Also looked at navigation ones as we discussed finding if the users garden is N/E/S/W facing | 0.5 | Yes
2 | 2023-05-02 | Asked group if we could try using a kanban app to delegate tasks as I struggle not having them listed out | 0 | Yes | I was thinking over the weekend and I was wondering how you guys feels about using some kind of kanban (like trello or whatever is free and easy for everyone) when we start dividing out work? I think I'm going to struggle trying to do it only on Slack, I find having tasks and stuff laid out a bit easier to keep track of things :) though tbh if everyone is pro Slack I can always use the one I use for work, so lmk your thoughts :blush:
2 | 2023-05-02 | Spoke with the group outside of the session to discuss our ideas. Discuss week 2 homework and combine aims and information for the app. Discussed how we could use the API to populate a database that we then use for the app as a static plant reference. Xanthe discussed Tkinter for possible user interface, pinned on Slack. Sarah added notes to report of what was discussed and Laura DP summarised on Slack for Aimee. | 1 | Yes
2 | 2023-05-03 | Spoke with the group outside of the session to discuss our ideas. Discussed how to structure the SQL database. Decide to make own plant api database using Chat GPT as Sarah suggested, a lot of APIs have lots of missing info and then we have more control over the data. We divide this up between ourselves. I take flowers 16 - 30. | 1 | Yes | Sarah started draft my sql backend and checked our plans with Youri.
2 | 2023-05-03 | Made post on Slack for everyone to choose what data they'll be requesting from ChatGPT. Used Sarah's qeury from bottom of report to make general query for ppl to use | 0.25 | Yes | Chat GPT requests (type: shrub, flower, vegetable, fruit) + range requesting:// Prompt for chatgpt: Could you create, in message form, text that I can copy into a .txt file to make a json dictionary? I would like a dictionary that I can use as an API. Populated with the following gardening details (key (4 letter code e.g. <<letter>>001 for <<type>> number 1), plant_name (common name), latin_name, class_name (vegetable, fruit, flower or shrub), light_conditions (favourable conditions e.g. shade or full sunlight), frequency_watering (frequency it needs watering in days), soil_type (clay, dry etc…), minerals_required (chemical names), planting_season (ideal planting season), growing_time (in days), toxicity (is it toxic to animals or humans). Can you populate this dictionary with the most popular UK <<type>>, in order but only <<type>> <<range>>, so that I can use it for a python app
2 | 2023-05-04 | Made Trello workspace for the group, made 2 boards initially: HW2 and Databases as these were the main sets of tasks we had. Shared with group so they can in workspace and add/edit tasks. Added in all tasks i could remember that we discussed over the past few meetings. Gave group screenshots on how to add eachother to the workspace as I was not in class on 05/05 | 0.25 | Yes
2 | 2023-05-05 | Began making flowchart + also made DB diagram to try understand how it would look for meeting on weekend | 1 | Yes | Finished this up day after as did not complete whilst at work
2 | 2023-05-05 | Discussed flowchart ideas on slack. BH to be PM. | 1 | Yes
2 | 2023-05-06 | Group was discussing getting json dict data into separate plant info tables on Slack. Spent some time on python to practice doing this. Got it to work but forgot a few columns we needed. | 3 | Yes | Used some of the code from the connecting database lesson to make a function, then used a for loop to iterate through the dictionary and add row by row in each table
2 | 2023-05-06 | Chatted with Sarah on 05/05, she suggested making poll on Slack to choose a day/time for weekend meeting to discuss report. Added simple poll to slack channel and made poll to get group availability. Settled on Sunday AM. | 0.25 | Yes
2 | 2023-05-07 | Spoke with the group outside of the session to review HW2: report and flowchart. Sarah had made base code for app, we all got to discuss this too. We decided on jobs for everyone to complete. Overall the aim was for everyone to run the base code and see how it was working, if there were errors and if there is anything that needs adding. Everyone was also given individual tasks depending on what they wanted to do/were interested in. We also discussed splitting the base code up in separate .py files, all agreed this would be helpful but was agreed we should try to troubleshoot the code first before splitting. Also discussed talking about group roles next week so everyone can chat about what they'd enjoy doing, and specifically how we could hand around the scrum master/PM role | 1.5 | Yes
2 | 2023-05-07 | Made post on Slack to distribute jobs. Updated trello with jobs, changed workspace to have 1 board as the other was not being used. Assigned teammembers to their tasks | 0.5 | Yes | Hey all! Following the meeting today we've now got base code for the app from Sarah. You can access this on the github repository Laura DP made (linked above) in the SDOWD branch. She's invited everyone so pls check your notifications if you can't see it yet :slightly_smiling_face: Base code allows the user to do the following atm: Creates tables + plant DB Populates plant tables (ID and requirements) User log in Search for plants to add to their logbook View their logbook We've delegated out some tasks today, but just to note if anyone wants to change their tasks or their tasks are unclear, reply to this and we can change/explain anything! It's not by force so don't hesitate to ask any Qs: @channel Everyone Check that the base code is working when you run it. You'll need to amend some parts of the code (for e.g., your mySQL password) before running. Note down any issues you run into with the code Note down what the code has, does and what you think it needs moving forward (a doc will be made on our google drive for us to use, Sarah will message when it's done) If you want to start working on any of the base code, make a branch first then start making any edits Check report doc to make sure you're happy with the content, check SWOT table too and make sure it reflects your skills :) @Laura DP With the base code, we've now made a mock up final flow chart in our google drive: https://docs.google.com/presentation/d/1CzO-OJCj6uDBGh7Djxs44SpyMO0KA5HKppwZ1-K4zO0/edit#slide=id.p We combined your's and Xanthe's flow to make this structure, and wanted to ask if you could make a final flow using the draft above pls? To note: There's one database with 4 tables API is separate to the back-end as we aren't making/storing the API data (we were thinking it's more in the middle where any python would be?) Pls add to the report when it's done :blush: Also would like to know if there's anything you'd like to work on coding-wise - have a look at some of the other tasks allocated and lmk if there's anything you'd like to research/work on and i'll add it here! @Xanthe Sharp Researching Weather APIs (seeing if they have Pollen, UV index too, seeing if we can request for past dates (?)) Testing accessing the API for info to answer user queries in the app @Aimee Szkolar In Sarah's base code, we need to add the try, except, finally clauses where we connect to the DB as atm we don't have them. We were talking about the kind we were working on in class with Youri, for e.g. before try we initialise the DB connection as None, and make sure it's always closed in the finally loop :slightly_smiling_face: But if you can find a better way try that! @Laura Cullen Going through base code and troubleshooting any minor issues Looking at weather APIs alongside Xanthe Outside of coding, please may you help finalising the report writing? Sarah will be putting a load of info in there so when she's done it'll need editing and finalising @Sarah Dowd Researching info to add to report Making a file for everyone to add notes about base code @Bethan Testing how we can make views for each user In theory will be used as the view the user sees when requesting to see their logbook Assuming we'd be making views from the Logbook and Plant_ID tables. Logbook table is made up of Log_ID, Plant_ID, User_ID and Date_Planted. Views filtered by User_ID and will show date planted, and will join w Plant_ID to display plant name. @Aimee Szkolar I know you said you like working on DBs so if you'd prefer this lmk, and we'll swap :slightly_smiling_face: We also discussed splitting the base code up in separate .py files, all agreed this would be helpful but was agreed we should try to troubleshoot the code first before splitting. Also discussed talking about group roles next week so everyone can chat about what they'd enjoy doing, and specifically how we could hand around the scrum master/PM role :smiling_face_with_3_hearts: Will be adding all these things to trello, might be amending the boards and stuff and would be happy for any help on how to structure it all so it's helpful for everyone!
3 | 2023-05-08 | Made branch off of Sarah's base code to add SQL query to create/replace view using user_id to filter logbook data, then joining other tables to show date planted, plant name. Ended up splitting all the code into functions, adding notes to separate areas of code (like datatbase functions, plant search etc) | 5 | Yes | Syntax for SQL making views per logbook: create or replace view {username}_logbook as select id.plant_name as 'Plant', log.date_planted as 'Date Planted' from plant_id id inner join logbook log on id.id = log.plant_id inner join users u on log.user_id = u.user_id where u.user_id = {user_id}
3 | 2023-05-09 | Spoke with the group outside of the session to divide code and tasks. Report completed and submitted. Made plan for group to split into 2 groups to do team coding. Group 1: finalising weather API code together + standardising json dict. Group 2: reviewing folder structure and discussing what code needs to be broken up futher into separate files/functions. | 1 | Yes
3 | 2023-05-10 | All group meeting to discuss how to do logbook task given by CFG. Settled on making tabs for each person. After, met with Laura C and Aimee to review folder structure Laura C made. All agreed folder structure was great, dvided up application folder between us to review code and break up further into separate files/functions to make testing easier. Spoke about using classes instead of functions, were discussing where we need classes/where they would be helpful. | 1 | Yes
3 | 2023-05-10 | Made Slack post for Laura C, Aimee and me so we had our tasks there. Put the split functions file I made on 06/05 as we were struggling to see eachother's work on Slack. | 0.25 | Yes | Tasks for @Aimee Szkolar , @Laura Cullen + @Bethan : Try to finish before Friday: Checking all functions in application folder and seeing what they're dependent on. File split: @Aimee Szkolar : Logbook (may try to add delete entry capability) @Laura Cullen : Login @Bethan : Search If needed, separate ll functions out into separate files if they're relying on multiple things that may be repeated throughout the code For the weekend: @Laura Cullen adding new API files to structure Going through all code on github and cleaning it up to get a base for everyone to work off of in the new file structure Split TBC
3 | 2023-05-11 | Look at search plants file. Split into separate .py files, made one search_plants file for main function to be stored. Could not get it working with classes, so have left it as functions for now. Think some bits still need to be separated but need to ask how the classes are working. Pushed to my branch next morning. | 2 | Yes
3 | 2023-05-12 | Group discussed when next to meet on Slack. Majority were available on Monday evening after class. | 0.25 | Yes
3 | 2023-05-12 | Made poll + discussion thread for the weekend as some team members wanted to to meet earlier. Suggested someone else could be PM + asked if we wanted to get rid of Trello as we haven't been active on it. | 0.25 | Yes
4 | 2023-05-15 | Group meeting outside of class. LC to be PM for week. BH to keep taking notes. Group to step back from trying to get code to run, group will be working on different sections and getting each of those working. Aim to finish this by Wednesday 17th. Aim to get sections to work in functions for now. API code finished, put to side until we begin to bring everything together. Agreed that we have a final draft of code by next Tues: 23rd May. Agreed to ask Amy (instructor) for advice on how to finalise code (navigation, classes etc) | 1 | Yes | 17.05.2023 Overall Laura C is new PM for this week! :partying_face: Bethan to keep typing up notes after meetings Group to step back from trying to get code to run, group will be working on different sections and getting each of those working. Aim to finish this by Wednesday 17th. Aim to get sections to work in functions for now API code finished, put to side until we begin to bring everything together Amy (hopefully!) to attend meeting between Thurs - Sat to help give us direction on: Navigation - atm group agreed on using numbers Using classes General advice on program Agreed that we have a final draft of code by next Tues: 23rd May Individual @Xanthe Sharp and @Sarah Dowd to begin working on the report/documentation. Aim to get this finished by EOD Sunday 21st @Aimee Szkolar to finalise logbook code by EOD Wed 17th @Bethan to finish search code (names and requirements) by EOD Wed 17th @Laura DP to work on additional search function (quiz search). Will work with @Bethan + @Aimee Szkolar so we can finalise out how logbook + search work together. Deadline (?) @Laura Cullen to continue to clean up code on github - finalise login, homepage, database by EOD Wednesday 17th
4 | 2023-05-16 | Finalised plant search functions, reduced files from 4 --> 3. Amended search by requirements code. Added in 2 helper functions to search for int requirements (days etc) or string requirments (soil type etc) | 2 | Yes
4 | 2023-05-19 | Ran through LDP's plant quiz code and wrote a possble helper function to help reduce some repeating code, posted on her thread on Slack | 0.5 | Yes
4 | 2023-05-20 | Meeting outside of class with Xanthe, Sarah and Laura DP. Discussed what we want to be aiming to do in the last week, where we're at now. Xanthe had completed testing for the weather page, Sarah had written up errors for all files and shared with group, Laura DP had made preogress on plant quiz. Agreed we wanted Amy's input on some assessment details. | 1 | Yes
5 | 2023-05-23 | Spent time at work trying to help Laura C trouble shoot errors that are raised when trying to access logbook and plant search, messaged on slack. Found some errors in logbook where we were importing an old version of the db connection | 1 | Yes
5 | 2023-05-24 | Spent morning going through whole app, seeing what each age was reliant on. Saw that plant search is not being used, suggested we remove it in favour of using search functions in logbook. Spent time amending logbook code to sort errors/add in small functionalities. Completed: Removing loop in menu, added date planted to logbook table + to local logbook dict, enabled user to view all logbook entries before searching for plant, commented out the file (to clearly mark out what's doing what - will be deleted later), removed view_logbook function as it was repeating display_logbook | 5 | Yes
5 | 2023-05-27 | Meeting outside of class with group, sorted final outstanding tasks, all group wanted to make sure we're not duplicating tasks. | 1 | Yes
5 | 2023-05-27 | Worked on database.py to add in try/except/finally blocks. Found that the way the connection had been set up meant that the connections were already being handled as i was getting errors about the connection alfready ebing closed. checked code in pymysql when error first came up. https://stackoverflow.com/questions/1984325/explaining-pythons-enter-and-exit helped explain about __enter__ and __exit__ in connect method and why the connections are safe. Found issues when i deleted my existing db and couldn't crate a new one when running the program. sorted the create_Database method and amended run.py so the db was created each time. | 3 | Yes

## Laura Depla-Phang Activity Log
Name: Laura Depla-Phang |  | Project Group (Name/Number): Bloom x labs // Software 2 // Group 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
9 | 2023-04-27 | Spoke with the group outside of the session to discuss our ideas. Ideas included a gardening app, horoscopes app, platform to arrange meeting at conferences. Made jam board of SWOT analysis for the team. | 30 mins | Yes
10 | 2023-05-01 | Researched possible plant APIs, other similar apps, functionality options. Added to SWOT board | 2 hrs | Yes
10 | 2023-05-02 | Spoke with the group outside of the lesson to share researched ideas. Confirmed plant based app. Discussed week 2 homework and combine aims and information for the app | 1 hr | Yes
10 | 2023-05-03 | Spoke with the group outside of the session to discuss our ideas. Decide to make own plant api database as some have lots of missing info and then we have more control over the data. We divide this up between ourselves and I take shrubs. | 1 hr | Yes
10 | 2023-05-04 | Generate shrubs for api. Update Trello | 1 hr | yes
10 | 2023-05-05 | Create report proposed flowchart for discussion | 1 hr | yes
10 | 2023-05-05 | Discussed ideas on slack. Bethan to be pm. | 1 hr | Yes
10 | 2023-05-07 | Setup/make GitHub repository and invite group to it | 30 mins | Yes
11 | 2023-05-08 | Review basic base code on own branch. Still needs to be merged to main. | 2 hrs | no
11 | 2023-05-09 | Design logo and give naming options | 1.5 hrs | no
11 | 2023-05-09 | Worked on final copy of flow diagram for week 2 homework report | 1 hr | Yes
11 | 2023-05-09 | Daily stand up meeting to share progress and divide next tasks, agreed all happy with report before SD submitted | 15 mins | Yes
11 | 2023-05-10 | Working on JSON file with plant data in | 3 hrs | No
11 | 2023-05-10 | Spoke with the group outside of the lesson to review current status/progress of weather APIs and JSON file | 45 mins | Yes
11 | 2023-05-11 | Working on JSON file with plant data in to add more data and incorporate amends discussed in meeting yesterday | 1.5 hrs | No
11 | 2023-05-11 | Made small piece of code to generate garden quote at program launch, researched online to find garden quotes and make text source file for code to reference | 1 hr | Yes
11 | 2023-05-12 | Finished editing JSON file - making entries consistent/uniform | 45 mins | Yes
11 | 2023-05-12 | Reverse filling in project activity log | 1 hr | Yes
11 | 2023-05-14 | Brain storming areas to contribute code. Put on group for feedback | 1 hr | Yes
11 | 2023-05-14 | Shared more ideas for group/project name | 30 mins | Yes
12 | 2023-05-15 | Working on plant quiz code | 5 hrs | No
12 | 2023-05-15 | Group meeting outside session to assign new PM (Laura C) taking over from Bethan. Confirmed API code completed, agreed to try and have draft of code for next Tuesday to allow time for testing. To work on quiz code and liaise with Bethan and Aimee. Agreed on plant app / group name suggestion: Group = x labs and app = Bloom | 1 hr | Yes
12 | 2023-05-16 | Working on plant quiz code and another logo variant | 5 hrs | No
12 | 2023-05-17 | Working on plant quiz code | 5 hrs | No
12 | 2023-05-18 | Working on plant quiz code - first draft shared with group in Slack | 5 hrs | Yes | Additional items to consider: * Prettier print out of generated result * Uploading result to logbook
12 | 2023-05-18 | Meet group outside of session to discuss.....
12 | 2023-05-19 | Received feedback on plant quiz code, work on improving it | 5 hrs | Yes
12 | 2023-05-20 | Meet group outside of session to discuss progress and next steps. Decide to try and run through all code on Monday after session and then confirm testing steps. Couldn't stay for all of meeting as planned as child unwell | 15 mins | Yes
12 | 2023-05-20 | Refactor plant quiz code a bit further to remove repeated code sections and store within helper functions. Uploaded plant quiz functions file and plant quiz run file to GitHub along with tiny amends to random quote file | 2 hrs | Yes
13 | 2023-05-23 | Working on creating test file for plant quiz | 3 hrs | No
13 | 2023-05-23 | Meet group outside of session to review run errors and troubleshoot. After some progress status updates, agreed to troubleshoot individually before regrouping. As not everyone could attend meeting, will create thread in Slack channel for others to update/share any pinch points | 30 mins | Yes
13 | 2023-05-24 | revise code amendments by SD, review general code changess, amend and continue tests. Added some text/screenshots to final work document | 5 hrs | No
13 | 2023-05-24 | Meet group outside of session to review project document, running status of program, menu system, remaining tasks | 1 hr | Yes
13 | 2023-05-25 | Work on testing, added further class to plant quiz file, uploaded revised files, reviewed LC's draft architecture diagram | 5 hrs | No
13 | 2023-05-26 | Carry on work on testing plant functions file and random quote file. Sourced ASCII art and ASCII art titles for sections in lieu of GUI | 7 hrs | Yes
13 | 2023-05-27 | Meet group outside of lessons to discuss outstanding items including fixing bugs, adding to project report, adding try, except to DB connections, complete testing and upload files | 1 hr | Yes
13 | 2023-05-27 | Battle GitHub error with 'unresolved conflicts' in one file which won't show when following their terminal instructions. Get files uploaded to main branch, message instructors with query from meeting, collate logos for voting, work on project report | 4 hrs | Yes
13 | 2023-05-28 | Final bits, checking everything is in order, fixed a repeated item in plan data API, liaise with team via Slack. Update logbook, add voted on logo to report, proof read. Created template and started headings for ppt presentation | 1 hr | Yes